**COST ACTION FP1301**

**“Innovative management and multifunctional utilization of traditional coppice forests - an answer to future ecological, economic and social challenges in the European forestry sector (EuroCoppice)”**

**notes of the 1ST Wg Meeting of the WP1: Definitions and Typology**

**CNR Ivalsa, Florence, IT**

**25 February 2014**

**Minutes Summary**

**Participants**

**WG Leader**: Dr. Dagnija Lazdiņa LSFRI Silava
**participants:**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **CTRY** | **Firstname** | **Lastname** | **Position in FP 1301** | **e-mail contact** | **WG** | **WG 1 attended** |
| AU | Marin | Kühmaier | WG member | martin.kuehmaier@boku.ac.at  | 3 | 1 |
| CH | Marco | Conedera | MC Member | marco.conedera@wsl.ch | 1 | 1 |
| DK | pieter | Kofman | STSM- coordinator, Substitute leader of WG 1 | pdkofman@gmail.com | 1 | 1 |
| IE | Enda  | Coates | WG member | ecoates@wit.ie | 3 | 1 |
| IT | Enrico | Marchi | Substitute STSM coordinator | enrico.marchi@unifi.it | 1 | 1 |
| LV | Dagnija | Lazdiņa | Leader WG 1 | dagnija.lazdina@silava.lv | 1 | 1 |
| UK | Rob  | Jarman  | WG member | rjarman@glos.ac.uk | 1 | 1 |
| CH | Radomir | Klavac | MC Member | klavac@mendelu.cz | 1 | 1 |
| IT | David | Travaguni |  | davide.travaguni@unifi.it |  | 1 |

1. Aim:

Milestones planned to reach within this WG1 :

* Milestone 2: Database of terminology - First year 2014
* Milestone 3: Coppice forest typology factsheet (WG 1). Second year – 2015
* WG1 will be responsible to the glossary which will be published in Third year -2016
1. Plan to reach aims, (*responsible persons*):
* To start with questionnaire for collecting, comparing and synthesizing the various expressions and definitions which are related to CFM in countries participating in action. To obtain data developed further to a glossary. *(P.Kofman & R.Klavac).*
* To create “living document” being continuously improved during the live time of the project by collecting, cross checking and compiling statistical and other data on coppice forests available in the participating countries and regions. To start put together information for creating of final fact sheet about European Coppice Forests at 2016.*(D.Lazdina)*
* To set a list of scientists and experts involved in action main field of expertise as well experts practitioners no involved in action, (planed to be post in year 1 at the first time and then continuously update until the end of the project)*(Enda Coates).*
* Posting and communicating the first draft of the glossary on the website *(P.Kofman & R.Klavac and native speakers).*
* Contributing to develop a terminology and a typology related of European Coppice Forests in close cooperation with WG 2 - leading in this task of typology *(D.Lazdina & R.Jarman).*
1. Possible format of dissemination *(coordinator D.Lazdina)*
* Presentation at international Poplar symposium.
* Articles in local country press.
* Paper “Coppice cross to Europe” in peer-reviewed journal.
* Online data base
* Lectures at training schools about terminology.
1. Full filing and translation of terminology in cooperation with lecturer of training schools and other working group members.
2. Possible working group meeting in Latvia to finish deliverables of 2014.